## Overview
Item | Summary
Last updated | 2026-05-14
Current template version | Compact academic portfolio: top navigation + left profile sidebar + restrained cards/entries. Main pages are About, CV, Publications, Talks, Research, Field Sites, Study, and Notes.
Current state | The core website structure is stable. About/CV, Publications, Talks, Research, Field Sites, Study, and Notes are aligned with the current template tone and GitHub Pages deployment flow.
Latest deployed commit before this checklist update | 05cd652 Standardize research project pages. This checklist update replaces the downloadable CV with v2, syncs Skills with the CV, and splits Talks into international/domestic conference sections.
Build / QA | Recent jekyll clean + jekyll build passed. Checked that CONTENT_EDITING_GUIDE.md is excluded from _site and project figure CSS is present in the built CSS.
Content strategy | Keep research projects and funded/participated research work inside Research. Add Side Projects only when there are public demos, code, tools, or personal experiments worth showing separately.
Recommended next direction | 1) Add actual project images/plots to images/projects/<project-key>/ 2) Insert figure blocks in the relevant project Markdown pages 3) Link Related Publications / Outputs to Publications entries 4) Prepare professor-specific contact email drafts.
File management | website_checklist.xlsx is the tracked local project checklist. task.md and website_checklist_backup.xlsx remain untracked.

## Done
Area | Work | Status | Priority | Owner | Evidence / Notes
Foundation | Jekyll/GitHub Pages build and deployment workflow | Done | High | Codex | Multiple pushes to master completed. Recent jekyll build passed.
Navigation | Top navigation structure | Done | High | User + Codex | CV, Publications, Talks, Research, Field Sites, Study, and Notes are active. Projects index was merged into Research.
Title / favicon | Browser title and favicon update | Done | Medium | Codex | Home title is Junyoung Park. Subpages use Page ¦ Junyoung Park. Academic-cap favicon was replaced by a sensing/signal icon.
Home / About | Intro, research interests, education, and work experience updates | Done | High | User + Codex | SHM, WIM/OBM, IoT sensing, AI-based data analysis, AI for Physical Systems, field bridge monitoring experience, and simplified sidebar degree reflected.
Home / About | Selected Work removed and Hobbies added | Done | Low | User + Codex | Swimming and drumming added.
Education | Degree labels and coursework cleanup | Done | High | User + Codex | M.S. in Civil Engineering (Structural Engineering), B.S. double major, dissertations, advisor, and coursework reflected.
CV | CV page content update | Done | High | User + Codex | Education, Research Interests, Skills, Work Experience, Publications, Honors, Scholarships, and Other activities updated. Last updated: October 2023.
Skills | Tool-oriented skills table | Done | High | User + Codex | Python, MATLAB, R, C, JavaScript/Node.js, SQL, PostgreSQL, PyTorch, TensorFlow, scikit-learn, pandas/NumPy, Abaqus, Simulink, SolidWorks, Altium, LabVIEW, NI DIAdem, AWS, Docker, Git, Premiere Pro.
Publications | Publication display cleanup | Done | High | User + Codex | Cited by, Scholar, Preprint/SSRN/Conference/Patent labels hidden. Linked titles are blue. Venue appears before authors.
Publications | Paper, patent, and author corrections | Done | High | User + Codex | Measurement under-review paper added/sorted, C. Min corrected, user name underlined, duplicate patent years removed.
Talks | Conference Presentations hierarchy | Done | Medium | User + Codex | All-bold style removed. Title-centered hierarchy aligned with publication title styling.
Research | Projects merged into Research | Done | High | User + Codex | Research page now serves as the project/system card index. Each card links to a detail page.
Research | Research card layout restored to compact grid | Done | Medium | User + Codex | Research cards use the compact grid. Added Sewer Monitoring Sensor System under Smart Sensing Systems and kept project cards linked to detail pages.
Research details | Detail page button/text cleanup | Done | Medium | User + Codex | Back to Projects and Related Publications buttons removed. Related Work wording changed to Related Publications.
Field Sites | Field Work converted to Field Sites | Done | High | User + Codex | Page rebuilt around actual sites and handled field data using clickable cards with left image slots and per-site detail pages. Intro text shortened.
Study | Study page prepared for future posts | Done | Medium | User + Codex | Current Topics cards added and Study Notes area added.
Notes | Notes list converted to cards | Done | Medium | User + Codex | Simple text list replaced by date/category/description note cards.
Other activities | Da Vinci Dream Discovery Program simplified | Done | Low | User + Codex | Volunteer & Service renamed Other activities and description reduced to one line.
Checklist | Checklist refreshed for current template version | Done | Medium | Codex | Done, Backlog, Next Actions, User Inputs, and Change Log updated.
Profile | ORCID link correction | Done | High | User + Codex | Updated profile/sidebar ORCID URL to https://orcid.org/0000-0002-3527-8534.
Research | Project-level Funded by placeholders | Done | Medium | User + Codex | Removed the global Research funding section and added Funded by placeholders to each project detail page using _data/project_funding.yml.
Education | Read Thesis PDF link | Done | Medium | User + Codex | Read Thesis now appears beside the M.S. dissertation title and opens Junyoung_Park_Master_Thesis.pdf.
Site chrome | 📡 favicon update | Done | Low | User + Codex | Replaced the SVG favicon with a radar emoji and added cache-busting query strings to favicon links.
About | PKM hobby chip | Done | Low | User + Codex | Added 🧠 PKM to the Hobbies chip list next to Swimming and Drumming.
Theme | Default light mode | Done | Medium | User + Codex | Changed first-visit/incognito behavior to use light mode unless the visitor has explicitly saved dark mode.
Profile | Seoul location marker | Done | Low | User + Codex | Added Seoul, South Korea to the sidebar profile card with a location marker.
About/CV | Research Interests wording cleanup | Done | Medium | User + Codex | Reorganized the three explanatory bullets into Infrastructure Monitoring, Sensing & Measurement Systems, and AI for Engineering Data.
Profile | Framed sidebar profile card | Done | Low | User + Codex | Added a subtle border, radius, background, and shadow to give the profile card more visual depth.
About/CV | Stronger Research Interests positioning | Done | Medium | User + Codex | Reframed the three bullets as Field-Validated Infrastructure Intelligence, Deployable Sensing & Edge-to-Cloud Measurement, and Physics-Aware AI for Engineering Systems.
Layout | Unified page start rhythm | Done | Medium | User + Codex | Adjusted topbar height, site top padding, grid alignment, and sticky profile offset so page titles and the profile card start consistently.
Research | Simplified project cards | Done | Medium | User + Codex | Restored period and two representative tag chips on Research cards after correction; cards show image area, title, period, summary, and tags.
About | Cleaner markdown-style structure | Done | Medium | User + Codex | Converted About education and work experience sections from custom entry blocks to a simpler markdown-like presentation.
Research | Restore project card period and tags | Done | High | User + Codex | Restored year/period and two representative tag chips on Research project cards after the previous overreach.
Site chrome | Chrome tab favicon assets | Done | High | User + Codex | Regenerated favicon PNG and ICO assets so Chrome can show the radar icon even when it uses non-SVG favicon files.
Site chrome | Galaxy favicon loading state | Done | High | User + Codex | Changed SVG, PNG, ICO, apple-touch, and root favicon.ico assets to the galaxy icon so Chrome can use it during loading and after load.
Site chrome | Transparent galaxy favicon | Done | Low | User + Codex | Removed the extra light backing from SVG/PNG/ICO/favicon assets so the galaxy icon appears without the white frame.
Field Sites | Add user-provided site names | Done | High | User + Codex | Updated Field Sites with Seongsan, Seosomun, Paldang, Cheongdam 1 Bridge, Saemangeum/Bongdong WIM, Koryeo Hwacha freight bearing monitoring, Seoul bus-only lane transportation monitoring, and Incheon Port.
Field Sites | Sites section on cards/details | Done | Medium | User + Codex | Added a Sites list to Field Sites cards and detail pages so concrete field locations are visible before data types.
Field Sites | Add location labels | Done | High | User + Codex | Added known location labels for bridge, WIM, Seoul bus-only lane, and Incheon Port field sites; left uncertain locations broad or blank.
Field Sites | Correct prefabricated field site | Done | High | User + Codex | Replaced Cheonma Remicon with Seoul Bus-Only Lane Transportation Monitoring in Field Sites cards and the detail page.
About | Refine Education and Work Experience layout | Done | Medium | User + Codex | Changed the About page Education and Work Experience sections from plain markdown blocks to compact dated summary entries.
About | Sharpen PhD contact positioning | Done | High | User + Codex | Added a memorable lead sentence and Research Fit bullets for AI/digital twin/reliability, smart sensing/IoT, and vehicle-bridge/transportation monitoring groups.
Research | Align Research page intro with contact positioning | Done | Medium | User + Codex | Updated the Research page intro to emphasize deployable sensing systems, field data, and engineering interpretation.
CV | Replace downloadable CV PDF | Done | High | User + Codex | Replaced assets/files/Junyoung_Park_CV.pdf with CV_Junyoung_Park_2026_v1.pdf and updated the CV page label to May 2026.
Mobile UI | Add collapsible mobile navigation | Done | High | User + Codex | Added a mobile-only menu toggle that collapses the navigation on narrow screens while preserving the desktop navbar.
Mobile UI | Compact mobile profile card | Done | High | User + Codex | Changed the mobile profile card to a smaller horizontal layout with reduced photo size and compact links.
Research | Standardize project detail pages | Done | High | User + Codex | Updated all Research project detail pages to use Problem, My Role, System / Methods, Field Deployment, Data / Outputs, and Related Publications / Outputs sections.
About/CV | Update advisor wording | Done | High | User + Codex | Changed the advisor line to the late Jongwoong Park on About and CV pages.
CV | Replace downloadable CV with v2 | Done | High | User + Codex | Replaced assets/files/Junyoung_Park_CV.pdf with CV_Junyoung_Park_2026_v2.pdf.
Skills | Sync skills table with CV | Done | High | User + Codex | Updated the homepage/CV skills table to match the Programming, ML, Software, Data, and Languages groups in the new CV.
Talks | Split conference presentations | Done | Medium | User + Codex | Separated Talks into International Conferences and Domestic Conferences using the existing venue classification.
Research | Add project figure styling | Done | High | User + Codex | Added reusable project figure and figure-grid CSS so project pages can display field photos, diagrams, and plots cleanly when content is added.
Assets | Create project image folders | Done | Medium | User + Codex | Added images/projects/<project-key>/ folders with .gitkeep placeholders for research project images and plots.
Documentation | Add content editing guide | Done | High | User + Codex | Added CONTENT_EDITING_GUIDE.md explaining where to edit project text, where to store images, and how to reference figures in Markdown/HTML.

## Backlog
Area | Work | Status | Priority | Owner | Notes
Research | Fill project-level Funded by entries | User needed | High | User + Codex | Add funder names, periods, and roles for each project in _data/project_funding.yml when the funding list is ready.
Research details | Strengthen representative project detail pages | Planned | High | User + Codex | Add public images, result figures, diagrams, and field evidence to WIM, OBM, Bridge Monitoring, Portable Sensing, etc.
Side Projects | Decide whether to add a separate section | Needs review | Medium | User | Add only if there are public demos, code, tools, or personal experiments. Keep separate from research projects.
Study / Notes | Write the second post | Planned | High | User + Codex | Possible topics: why field-deployable sensing systems are central to the portfolio, or a WIM/OBM study note.
Study / Notes | Add pagination when the number of posts grows | Later | Low | Codex | Use Jekyll pagination or category pages once there are roughly 10-15+ posts. Current card list is enough for now.
CV | Replace latest CV PDF | User needed | High | User | The web CV page has been updated, but the PDF should be replaced when the latest file is ready.
Field Sites | Add public field images and captions | User needed | Medium | User + Codex | Only use public/non-confidential material. Site, sensor installation, or measurement photos would improve credibility.
Publications | Final cross-check between CV and Publications | Planned | Medium | User + Codex | Keep preprints out of CV. Re-check for missing journal articles or status changes.
Visual QA | Real browser and mobile QA | Planned | Medium | Codex | Check favicon cache, card spacing, mobile nav, text overflow, and page rhythm after deployment.
Search Console | Monitor indexing and sitemap status | Monitoring | Medium | User | Check indexing status of important URLs and sitemap submission.
Education | Upload M.S. thesis PDF | Done | Medium | User | Completed. PDF is available at assets/files/Junyoung_Park_Master_Thesis.pdf.
Field Sites | Add field-site photos | User needed | High | User + Codex | Add public/non-confidential images for Seongsan, Seosomun, Paldang, Cheongdam 1 Bridge, Saemangeum, Bongdong, Koryeo Hwacha, Cheonma Remicon, and Incheon Port.

## Next Actions
Order | Action | Concrete steps | Owner | Timing
1 | Collect participated research project info | Gather official Korean/English title, period, agency, role, personal contribution, outputs, and public/confidential status. | User | Recommended first
2 | Fill project-level funding data | Use _data/project_funding.yml to add funders per project detail page; no separate Research-wide funding section is currently needed. | User + Codex | After funding list is ready
3 | Improve representative project details | Choose 1-2 pages among WIM, OBM, or Bridge Monitoring and add images, result examples, and concise evidence. | User + Codex | High-impact next improvement
4 | Write the next Study/Notes post | Use Study for technical learning notes and Notes for personal/research logs. Start short. | User + Codex | Any time
5 | Replace latest CV PDF | Update assets/files/Junyoung_Park_CV.pdf with a file matching the current CV page. | User | When file is ready
6 | Run browser/mobile QA | After deployment, check favicon/title, Research grid cards, Field Sites image cards, Study/Notes cards, and mobile width behavior in Chrome. | User + Codex | After next deployment

## User Inputs
Needed input | Need level | Status | Priority | Notes
Project-level funding details | Required for Funded by sections | User needed | High | For each project: funder/agency name, period, role, and whether it can be publicly shown.
Side project candidates | Optional | User needed | Medium | Links, code, demos, screenshots, or descriptions if a separate Side Projects section is desired.
Representative project images/diagrams | Optional but valuable | User needed | High | Useful for WIM, OBM, Bridge Monitoring, Portable Sensing, and Field Sites cards/detail pages.
Latest CV PDF | As needed | User needed | High | Needed to align downloadable PDF with the current CV page.
Next Study/Notes topic | Optional | User needed | Medium | Codex can draft once a topic is chosen. Study = technical note; Notes = personal/research log.
Publication/patent status updates | Optional | User needed | Medium | Update when under review, accepted, published, application, or registration status changes.
Post-deployment screen feedback | Optional | User needed | Low | Chrome may cache favicon. Screenshots help if spacing or icon updates look stale.
M.S. thesis PDF | Required for active thesis link | Received | Medium | Received and linked as assets/files/Junyoung_Park_Master_Thesis.pdf.

## Change Log
Date | Change | Details | Owner
2026-05-11 | Checklist rebuilt | Reconstructed the checklist from the current website state. | Codex
2026-05-14 | About/CV content overhaul | Updated intro, Research Interests, Education, Work Experience, Skills, Scholarships, and Other activities. | User + Codex
2026-05-14 | Publications/Talks cleanup | Removed helper labels, adjusted linked titles, venue order, and Talks hierarchy. | User + Codex
2026-05-14 | Research structure consolidated | Merged Projects index into Research while preserving detail page links. | User + Codex
2026-05-14 | Field Sites added | Converted Field Work into Field Sites with categorized site/data cards. | User + Codex
2026-05-14 | Skills/Favicon update | Added tool-oriented skills table and updated favicon/title/manifest assets. | User + Codex
2026-05-14 | Study/Notes layout update | Added Study topic cards and Notes card list. Research temporarily changed to horizontal cards, later restored to grid. | User + Codex
2026-05-14 | Checklist refreshed | Updated Done, Backlog, Next Actions, User Inputs, and Change Log for the current template version. | Codex
2026-05-14 | Field Sites horizontal cards correction | Restored Research cards to the previous compact grid and applied the horizontal one-row card style to Field Sites instead. | User + Codex
2026-05-14 | ORCID and clickable Field Sites update | Updated ORCID link and converted Field Sites cards into links to per-site detail pages. | User + Codex
2026-05-14 | Skills PostgreSQL update | Added PostgreSQL to the tool-oriented skills table. LabVIEW was already included and remains listed under Measurement & DAQ. | User + Codex
2026-05-14 | Field Sites image slots and AI keyword update | Added left-side image slots to clickable Field Sites cards and replaced AI-based Signal Interpretation with AI for Physical Systems. | User + Codex
2026-05-14 | Field Sites intro and Smart Concrete period update | Shortened Field Sites intro, corrected Smart Concrete Sensing System period to 2020-2021, and simplified sidebar degree text. | User + Codex
2026-05-14 | Thesis button and funding placeholder | Added a disabled Read Thesis pill beside the M.S. degree and created a Funded Research section backed by funding.yml. | User + Codex
2026-05-15 | M.S. thesis PDF linked | Copied the master thesis PDF into assets/files and connected the Read Thesis button on About and CV. | User + Codex
2026-05-15 | Project-level funding and sewer sensor update | Moved funding placeholders from Research index to each project detail page, added Sewer Monitoring Sensor System, and moved Read Thesis beside the dissertation title. | User + Codex
2026-05-15 | Favicon and hobbies update | Changed the browser/site favicon to 📡, added favicon cache busting, and added 🧠 PKM under Hobbies. | User + Codex
2026-05-15 | Theme and research interests refinement | Set the site default to light mode, added Seoul to the profile card, and unified the Research Interests explanatory bullets on About and CV. | User + Codex
2026-05-15 | Profile card and research positioning | Added visual framing to the sidebar profile card and sharpened Research Interests wording for a stronger international academic audience. | User + Codex
2026-05-15 | Layout rhythm and Research cards | Aligned page/profile vertical rhythm, kept the profile sticky, kept Research card period/tag chips after correction, and cleaned the About page section structure. | User + Codex
2026-05-15 | Research card correction | Restored the Research project card period and two tag chips; this corrects the previous unintended removal. | User + Codex
2026-05-15 | Chrome tab favicon assets | Regenerated favicon-32x32, favicon-192x192, favicon-512x512, favicon.ico, and apple-touch-icon with the radar icon. | User + Codex
2026-05-15 | Galaxy favicon update | Changed the Chrome tab favicon from radar to galaxy across SVG, PNG, ICO, apple-touch, and root favicon.ico assets, with cache-busted links. | User + Codex
2026-05-16 | Transparent galaxy favicon | Removed the extra light favicon backing and regenerated SVG, PNG, ICO, apple-touch, and root favicon.ico assets with a transparent galaxy icon. | User + Codex
2026-05-16 | Field Sites concrete site update | Added the user-provided field site names to Field Sites cards/detail pages and replaced the generic bridge campaigns page with Cheongdam 1 Bridge. | User + Codex
2026-05-16 | Field Sites locations and About layout | Added known field-site locations, corrected the prefabricated field site to Seoul bus-only lane monitoring, removed Cheonma Remicon from rendered content, and refined About page Education/Work Experience entries. | User + Codex
2026-05-18 | PhD contact positioning copy | Sharpened the About lead sentence, added Research Fit bullets for prospective advisor audiences, and aligned the Research page intro. | User + Codex
2026-05-18 | Updated downloadable CV | Replaced the site CV PDF with the May 2026 version and updated the visible CV page date. | User + Codex
2026-05-18 | Mobile navigation and profile layout | Added a mobile menu toggle and compact mobile profile-card styling without changing the desktop layout. | User + Codex
2026-05-18 | Standardized Research detail pages | Reworked all Research project detail pages into a consistent structure and updated advisor wording to the late Jongwoong Park. | User + Codex
2026-05-18 | CV v2, skills, and Talks split | Replaced the downloadable CV with v2, synced the Skills table with the CV, and split Talks into international/domestic conference sections. | User + Codex
2026-05-18 | Project image folders and editing guide | Added project image folders, reusable project figure CSS, and a local content editing guide for future writing/image work. | User + Codex